## Slide 1
Mile Post 164.5 Incident
Lessons Learned Presentation to ADEC
Hank Herglotz, Colville Safety Manager

## Slide 2: Incident Overview
Date: January 09, 2017
Time: 3:15 p.m.
Location: Mile Post 164.5 of the Richardson Highway
What Happened: A Semi-Truck with a Double Set of Trailers Departed the Roadway
Root Cause: Driver Steered Into Over-Plow of Road
MP164.4 Richardson Hwy

## Slide 3: Mile Post 164.5 Incident

## Slide 4: Incident Outcome
Driver Injured with 18 Lost Days of Work
Lead Trailer, Forward Compartment breeched upon impact
Approximately 4000 Gallons of ULSD Spilled on the roadway
Tractor, Lead Trailer & Pup Trailer Damaged
Recovery Operations
Environmental Clean-Up

## Slide 5: Incident Outcome…Cont’
Notes: Compartment breech of the Lead Trailer

## Slide 6: Incident Outcome…Cont’
Notes: Left Photo - Damage of Semi Truck
Right Photo – Damage to the aft and forward section of the Pup Trailer
Estimated Cost of Repair – Pushing in the upward amount of $100,000

## Slide 7: Timeline of Events
9 Jan – Incident Occurred
  Activated Incident Command; Agencies notified
  On site recovery operations initiated
10 Jan – Response Plan in place
11 Jan – Mobilized Equipment to Site
  Executed Response Plan

## Slide 8: Site Reconnaissance
5017760 -- Vehicle 32-123 right steer tire blow out
Survey Environmental
  Sensitive Areas
  Terrain
  Critical Infrastructure
Potential Impact
Resources Required
  Equipment
  Personnel
Notes: Investigation of site allowed accurate delineation of site, much more effective in the long run. When able this is advisable.

## Slide 9: What Went Well?
Tanker Recovery Operation
Response Van Availability
Site Investigation
Delineation of Impacted Area
Snow/Free Product Removal
Excavation Progressed Smoothly
No Injuries or Incidents!
Notes: Tanker Recovery Operation
- Swift response, Very good collaboration
- Spill kits from other companies (Buckets for Leaks and Absorbs for Free standing)
- Lodge owners – Meyers lake lodge.
Response Van - Available and loaded with equipment
Site Investigation – Went well (Minor Comments in Equipment Slide)
Delineation of Site
- Product remained in a relatively small area
- No threat of Waterways
- Just slightly under road prism
Snow/Free product Removal initially/recovery of product later
Management of Dig
- simultaneous operations (More efficient/Increased risk)

## Slide 10: Challenges / Surprises
Dog Race in Vicinity During Spill Response
3rd Party Insurance Consultant assigned as follow-on Incident Commander
  Unfamiliar with Alaska’s Operating Conditions
  Stakeholder limited in Contractor Selections
Equipment
  Availability, Quality, Condition
Environmental Factors
Notes: Spill occurred right in the middle of a Dog Race Event
Concern of spill impact for event
Lodging for spill personnel at Meier’s Lake Lodge
Assigned by 3rd Party Insurance
Unfamiliar with Alaska’s Operating Conditions
Stakeholder not involved in Selection Process
Communication between agencies
Incident Site & Local Terrain
Culvert in road prism
Planned road construction in the future
Limited on the Dig. 1:1 Ratio
Truck turn around distance
Equipment
- Excavator Bucket
- High Quality GPS
Environmental Factors
Weather Conditions
Wildlife concerns (Mylar in response trailer)

## Slide 11: Milestones
Excavated Contaminated Soil & Materials from Site
Backfilled with Approved Gravel Source
Monitoring backfill area for erosion, Future Plans to be Determined
Insert Photo Here of Google shot
Notes: Excavated materials were thermally treated in North Pole
Will monitor for erosion of backfilled area, further work not expected until road construction
Monitor Site Until Spring, When Operations Resume only monitor for erosion of backilled area, further work not expected until road construction
Excavated Materials On- Site Removed and thermally treated in North Pole
Backfilled with Approved Gravel from BLM pit at Miers Lake, its very sandy which is an issue from erosion standpoint, local backfill important to limit importation of weeds
Incident On-Going , Further Plans to be Determined major work complete, surface restoration likely needed

## Slide 12: Simple “Take-Aways”
Communication
  Up channel Information
  Agencies (ADEC, BLM, DOT, etc.)
  Internal Communication
Establish timeline of events
Single Gatekeeper
  Information Flow, Catalog & Retrieve
Photographs, Reports & Statements

## Slide 13
Questions?